## PEA & RA
Preliminary Engagement Activities & Risk Assessment
CHANGE ORDER ITEMS INCLUDED:
| Change Order Area | Change Order Trigger |  | Trigger Specifics
| Milestones missed | AAE - Approach to Significant Risk |  | 154
| Milestones missed | AAE - Gain Understanding of IT |  | 154
| Milestones missed | AAE - Estimates |  | 154
| Milestones missed | AAE - Perform Other Risk Assessment |  | 154
| Milestones missed | AAE - Determining Significant Accounts/Disclosures |  | 154
| Milestones missed | AAE - Component Materiality |  | 154
| Milestones missed | AAE - Determine Group Materiality & Scoping |  | 154
| Milestones missed | AAE - Engagement Set Up |  | 184
| Milestones missed | AAE - Understand the Entity and its Environment |  | 154
| Milestones missed | AAE - Materiality |  | 184
| Milestones missed | AAE - Planning Analyticals |  | 123
| Milestones missed | AAE - Hold Risk Assessment & Planning Discussion |  | 154
BUDGET OVERAGE HOURS TO DATE:
| Grade | Average Rate per Hour | Hours Billed | Unplanned Costs @ Standard RPH
Audit
| Partner | 1356 | 6 | 8136
| Manager | 1018 | 6 | 6108
| Senior Associate | 868 | 6 | 5208
| Associate | 568 | 6 | 3408
Tax
| Partner | 6 | 6 | 36
| Senior Associate | 6 | 6 | 36
| TOTALS |  | 36 | 22932
ADDITIONAL EXPENSES:
| Additional Expenses |  |  | 12
| Total Overage Costs |  |  | 22944
| Total Billed |  |  | 4

## MA
Managing the Audit
CHANGE ORDER ITEMS INCLUDED:
| Change Order Area | Change Order Trigger |  | Trigger Specifics
| Milestones missed | AAE - Experts, Specialists and Internal Audit |  | 154
| Milestones missed | Submit finalized budget in the Engagement Management Tool |  | 123
| Milestones missed | AAE - Complete Software Audit Tools Engagement Profile |  | 154
BUDGET OVERAGE HOURS TO DATE:
| Grade | Average Rate per Hour | Hours Billed | Unplanned Costs @ Standard RPH
Audit
| Manager | 1018 | 6 | 6108
| Senior Associate | 868 | 6 | 5208
| Associate | 568 | 6 | 3408
Other
| Manager | 6 | 6 | 36
| TOTALS |  | 24 | 14760
ADDITIONAL EXPENSES:
| Additional Expenses |  |  | 12
| Total Overage Costs |  |  | 14772
| Total Billed |  |  | 4

## 3 KAA & RAA
3 Key Audit Areas & Remaining Audit Areas
CHANGE ORDER ITEMS INCLUDED:
| Change Order Area | Change Order Trigger |  | Trigger Specifics
| Milestones missed | AAE - Design Estimates Audit Procedures |  | 62
| Milestones missed | AAE - Plan IT Considerations |  | 62
BUDGET OVERAGE HOURS TO DATE:
| Grade | Average Rate per Hour | Hours Billed | Unplanned Costs @ Standard RPH
Audit
| Manager | 1018 | 6 | 6108
| Senior Associate | 868 | 6 | 5208
| Associate | 568 | 6 | 3408
ITAS
| Partner | 6 | 6 | 36
| Senior Manager | 6 | 6 | 36
Other
| Manager | 6 | 6 | 36
| TOTALS |  | 36 | 14832
ADDITIONAL EXPENSES:
| Additional Expenses |  |  | 12
| Total Overage Costs |  |  | 14844
| Total Billed |  |  | 4

## CA
Completion Activities
CHANGE ORDER ITEMS INCLUDED:
| Change Order Area | Change Order Trigger |  | Trigger Specifics
BUDGET OVERAGE HOURS TO DATE:
| Grade | Average Rate per Hour | Hours Billed | Unplanned Costs @ Standard RPH
| TOTALS |  | 0 | 0
ADDITIONAL EXPENSES:
| Additional Expenses |  |  | 10
| Total Overage Costs |  |  | 10
| Total Billed |  |  | 4

## IRA
Interim Review Activities
CHANGE ORDER ITEMS INCLUDED:
| Change Order Area | Change Order Trigger |  | Trigger Specifics
BUDGET OVERAGE HOURS TO DATE:
| Grade | Average Rate per Hour | Hours Billed | Unplanned Costs @ Standard RPH
| TOTALS |  | 0 | 0
ADDITIONAL EXPENSES:
| Additional Expenses |  |  | 10
| Total Overage Costs |  |  | 10
| Total Billed |  |  | 4